## Test Cases
TEST CASE ID | FEATURE TYPE | COMPONENT | TEST SCENARIO | PRE-REQUISITE | STEPS TO EXECUTE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS | COMMENTS | BUG ID | EXECUTED BY
BasicWebPageDesign_TC_OO1 | UI | Home Page | Verify user is able to see the webpage with basic components | Install and setup visual studio code. | 1.Enter UrL and click go 2.Verify navbar with components like Home,Predict,Login is available | http://127.0.0.1:5000/ | Basic navbar in the webpage should be displayed | As expected but redirection is not possible | PASS | Decent webpage is created. |  | Keerthana M Krishnapriya S Maheeraj J F Mannoj @ Ramnadan A
BasicWebPageDesign_TC_OO2 | Functional | Home Page | Verify redirection is possible when any components in navbar is clicked | Install python,flask and necessary packages | 1.Enter UrL and click go 2.Click the components in navbar | http://127.0.0.1:5000/ | Redirect to the respective pages when user click the component in the navbar | Logout button is not redirected instead it throws an error | FAIL | Page not found error is thrown | BUG - 1 | Keerthana M Krishnapriya S Maheeraj J F Mannoj @ Ramnadan A
LoginPage_TC_OO3 | UI | Login/Register Page | Verify whether login and register page is visible with required fields when clicked the URL | Integrate webpage with flask | 1.Enter URL and click enter to go. 2.Application should display login and register tabs with respective fields. | http://127.0.0.1:5000/ | Application should show below UI elements: 1.LOGIN tab a.User Id b.Password 2.REGISTER tab a.Email b.User Id(required) c.Password(required) | Working as expected | PASS | Successfully created login/register page. |  | Keerthana M Krishnapriya S Maheeraj J F Mannoj @ Ramnadan A
LoginPage_TC_OO4 | Functional | Login/Register Page | Verify whether it is possible to enter the valid details. |  | 1.Enter URL(http://127.0.0.1:5000/) and click enter to go. 2.Click register tab 3.Enter invalid email id 4.click register button | Email : Kayps17@gmail.com | Should show an error as '@' is missing in email id. | Working as expected | PASS |  |  | Keerthana M Krishnapriya S Maheeraj J F Mannoj @ Ramnadan A
LoginPage_TC_OO5 | Functional | Login/Register Page | Verify when existing user try to register it throws an error message "User already exists". |  | 1.Enter URL(http://127.0.0.1:5000/) and click enter to go. 2.Click Register tab. 3.Enter already registered username. 4.click Register button | Username : Krishnapriya S Password : Test | Should show an validation error as user already exists. | Working as expected | PASS |  |  | Keerthana M Krishnapriya S Maheeraj J F Mannoj @ Ramnadan A
LoginPage_TC_OO6 | Functional | Login/Register Page | Verify user is able to log into application with invalid credentials. |  | 1.Enter URL(http://127.0.0.1:5000/) and click enter to go. 2.Enter invalid/valid username in respective field. 3.Enter invalid/valid password. 4.click login button | Username : Krishnapriya S Password : Test | Application should show 'Invalid user or password ' validation message. | Working as expected | PASS |  |  | Keerthana M Krishnapriya S Maheeraj J F Mannoj @ Ramnadan A
LoginPage_TC_OO7 | Functional | Login/Register Page | Verify user is able to log into application with valid credentials. |  | 1.Enter URL(http://127.0.0.1:5000/) and click enter to go. 2.Enter valid username in respective field. 3.Enter valid password. 4.click login button | Username : Krishnapriya S Password : Test | User should navigate to homepage. | Working as expected | PASS | Successfully logged in . |  | Keerthana M Krishnapriya S Maheeraj J F Mannoj @ Ramnadan A
HomePage_TC_OO8 | UI | Home Page | Verify user is able to see information on parkinsons disease. |  | 1.Enter URL(http://127.0.0.1:5000/) and click enter to go. 2.Login with valid credentials. 3.Click Home button in navbar | Username : Krishnapriya S Password : Test | User should be able to see information on parkinsons disease such as symptoms, cause,treatment. | Working as expected | PASS |  |  | Keerthana M Krishnapriya S Maheeraj J F Mannoj @ Ramnadan A
PredictPage_TC_OO9 | UI | Predict Page | Verify user is able to redirect to predict page . |  | 1.Enter URL(http://127.0.0.1:5000/) and click enter to go. 2.Login with valid credentials. 3.Click Predict button in navbar | Username : Krishnapriya S Password : Test | User is able to see choose and predict button in predict page with an NOTE message | Working as expected | PASS |  |  | Keerthana M Krishnapriya S Maheeraj J F Mannoj @ Ramnadan A
PredictPage_TC_O10 | Functional | Predict Page | verify user is able to upload the image and get the result | Build an ML model for parkinsons disease prediction | 1.Enter URL(http://127.0.0.1:5000/) and click enter to go. 2.Login with valid credentials. 3.Click Predict button in navbar 4.Click Choose button to upload an essential image. 5.Click Predict button to get the result. |  | User is able to upload pic from the computer and review the output | Working as expected | PASS | Predicted accurately. |  | Keerthana M Krishnapriya S Maheeraj J F Mannoj @ Ramnadan A
Logout_TC_011 | Functional | Logout | Verify user is able to logout | Login page is needed. | 1.Enter URL(http://127.0.0.1:5000/) and click enter to go. 2.Login with valid credentials . 3.Click Logout button in navbar. | Username : Krishnapriya S Password : Test | User is able to click Logout button and redirect to Login/Regster page | Working as expected | PASS | BUG 1 is resolved |  | Keerthana M Krishnapriya S Maheeraj J F Mannoj @ Ramnadan A

## Test Scenario
TEST SCENARIOS
1 | Verify user is able to see login and register page
2 | Verify user is able to register
3 | Verify user is able to login to the application
4 | Verify user is able to navigate in home page
5 | Verify user is able to see information about parkinsons disease on homepage
6 | Verify user is able to upload the image on predict page
7 | Verify user is able to see the output
8 | Verify user is able to logout